## ABS_OCE_Milestone
| Milestone | Milestone 0 : Account Details , Smart Routing , Downloads , Query box , Related Questions, Citations |  |  | Milestone 1 : Top KPI , Action on KPI , Top Accounts ,Account Search , Citations, follow up questions , Query Box. QnA ABS : 5 Questions QnA OCE: 5 Questions |  |  | Milestone 2 ABS Milestone : Parent Acc Details , Opnal Readiness ,AccPerformance OCE Milestone : Alerts Journey QnA ABS: 2 Questions QnA OCE: 2 Questions |  |  |  | Milestone 3 : Territory Insights : Filtering , Sorting , Download table QnA ABS: 2 Questions QnA OCE: 2 Questions |  |  | Milestone 4 : Account hierarchy QnA ABS: 3 Questions QnA OCE: 2 Questions
Week starting
| ABS | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
| Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Team 1 | Home Screen
Account Insights
Team 1 | Territory Insights
Suggested Questions
Data Assessment and Data model designing
ETL - Processed data creation
Semantic Layer Development
| Gen Ai Layer Development |  |  |  |  | 5 |  | 2 | 2 |  | 3
Dev Environment - Data Migration
QA Environment - Data Migration
QA Deployment & Testing
Home Office user feedback incorporation
Resolve Vulnerability / Load Testing
Prod Environment - Data Migration
Prod deployment
Beta testing
National Launch
| OCE | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
| Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Home Screen
Team 2 | Account Insights
Territory Insights
Team 2 | Suggested Questions
Data Assessment and Data model designing
ETL - Processed data creation
Semantic Layer Development
| Gen Ai Layer Development |  |  |  |  | 5 |  | 2 | 2 | 2
Dev Environment - Data Migration
QA Environment - Data Migration
QA Deployment & Testing
Home Office user feedback incorporation
Resolve Vulnerability / Load Testing
Prod Environment - Data Migration
Prod deployment
Beta testing
National Launch

## Resource Loading
ABS
Name | Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Shivang | Solution Owner | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35%
Mohammad Shadan | Front End 1 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Mohammad Saif | Front End 2 | 2: 50%; 3: 50%; 4: 50%; 5: 50%; 6: 50%; 7: 50%; 8: 50%; 9: 50%; 10: 50%
Sunil Kumar | Back End 1 | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Vijet Hegde | Back End 2 |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 25% | 25% | 25% | 25%
| Gen Ai 1 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50%
| Gen Ai 2 | 4: 50%; 5: 50%; 6: 50%; 7: 50%; 8: 50%; 9: 50%; 10: 50%
Vinay | Data Engineer 1 | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Lakshmikanth (0.5) + TBD (0.5) | Data Engineer 2 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Shaik Khaja | Dev Ops | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
| QA/BA | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Jayaprakash L | PM/SM | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35%
Kishore | Tech Lead Offshore | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
Subidya | Tech Lead Onsite | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
OCE
Name | Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Samarth | Solution Owner | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35%
Sandeep Patil | Front End 1 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Mohammad Saif | Front End 2 | 2: 50%; 3: 50%; 4: 50%; 5: 50%; 6: 50%; 7: 50%; 8: 50%; 9: 50%; 10: 50%
Pavan Padakki | Back End 1 | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Vijet Hegde | Back End 2 |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 25% | 25% | 25% | 25%
| Gen Ai 1 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50%
| Gen Ai 2 | 4: 50%; 5: 50%; 6: 50%; 7: 50%; 8: 50%; 9: 50%; 10: 50%
Vinay | Data Engineer 1 | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Lakshmikanth (0.5) + TBD (0.5) | Data Engineer 2 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Shaik Khaja | Dev Ops | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
| QA/BA | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Jayaprakash L | PM/SM | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35%
Kishore | Tech Lead Offshore | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
Subidya | Tech Lead Onsite | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%

## Kishore (OCE Costs)
OCE
Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Solution Owner | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35%
Front End 1 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Front End 2 |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Back End 1 | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Back End 2 |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 25% | 25% | 25% | 25%
Gen Ai 1 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50%
Gen Ai 2 |  |  |  | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Data Engineer 1 | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Data Engineer 2 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Dev Ops | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
QA/BA | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
PM/SM | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35%
Tech Lead Offshore | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
Tech Lead Onsite | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Solution Owner | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 33600
Front End 1 | 3000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 93000
Front End 2 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
Back End 1 | 1500 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 91500
Back End 2 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 33000
Gen Ai 1 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 60000
Gen Ai 2 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
Data Engineer 1 | 3000 | 4500 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 91500
Data Engineer 2 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 66000
Dev Ops | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 48000
QA/BA | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 48000
PM/SM | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 33600
Tech Lead Offshore | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 24000
Tech Lead Onsite | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 9600
679800

## Kishore (ABS Cost)
[17 empty] | Beta Launch |  | National Launch
Name | Cost | Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Shivang | 34500 | Solution Owner | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 15%
Mohammad Shadan | 93000 | Front End 1 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Mohammad Saif | 27000 | Front End 2 | 2: 50%; 3: 50%; 4: 50%; 5: 50%; 6: 50%; 7: 50%; 8: 50%; 9: 50%; 10: 50%
Sunil Kumar | 91500 | Back End 1 | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Vijet Hegde | 33000 | Back End 2 |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 25% | 25% | 25% | 25%
- | 60000 | Gen Ai 1 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50%
- | 21000 | Gen Ai 2 | 4: 50%; 5: 50%; 6: 50%; 7: 50%; 8: 50%; 9: 50%; 10: 50%
Vinay | 91500 | Data Engineer 1 | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Lakshmikanth (0.5) + TBD (0.5) | 66000 | Data Engineer 2 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Shaik Khaja | 48000 | Dev Ops | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Apoorva/Akshat | 48900 | QA/BA | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 15%
Jayaprakash L | 33600 | PM/SM | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35%
Kishore | 24000 | Tech Lead Offshore | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
Subidya | 9600 | Tech Lead Onsite | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
681600

## Suggested (Combined)
TOTAL COST
Common Resources | 974100 |  | Milestone 0 : Account Details , Smart Routing , Downloads , Query box , Related Questions, Citations |  |  | Milestone 1 : Top KPI , Action on KPI , Top Accounts ,Account Search , Citations, follow up questions , Query Box. QnA ABS : 5 Questions QnA OCE: 5 Questions |  |  | Milestone 2 ABS Milestone : Parent Acc Details , Opnal Readiness ,AccPerformance OCE Milestone : Alerts Journey QnA ABS: 2 Questions QnA OCE: 2 Questions |  |  |  | Milestone 3 : Territory Insights : Filtering , Sorting , Download table QnA ABS: 2 Questions QnA OCE: 2 Questions |  |  | Milestone 4 : Account hierarchy QnA ABS: 3 Questions QnA OCE: 2 Questions
Team Member | Cost | Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Subidya | 7800 | Tech Lead Onsite | 10% | 10% | 10% | 10% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 5% | 5%
Kishore | 9300 | Tech Lead Offshore | 15% | 15% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 0% | 0% | 0%
Vinay | 69000 | Data Engineer 1 | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 75% | 75% | 75% | 50% | 50% | 50% | 50% | 25% | 25% | 25% | 25%
Lakshmikanth | 52800 | Data Engineer 2.1 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 25% | 25% | 25% | 25% | 15% | 15% | 0% | 0%
Jayprakash | 40800 | PM/SM | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 25% | 25% | 15% | 15% | 0% | 0%
Vijet Hegde | 32100 | Back End 2 | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 25% | 20% | 20% | 20% | 0% | 0% | 0% | 0%
Shaik Khaja | 19200 | Dev Ops | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 0% | 0%
Padmanabh/Apoorva/Akshat | 129600 | QA/BA | 160% | 160% | 160% | 160% | 160% | 160% | 160% | 160% | 160% | 160% | 160% | 100% | 100% | 100% | 50% | 50% | 0% | 0%
360600
ABS Team
Name | Cost | Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Shivang | 44400 | Solution Owner | 50% | 50% | 50% | 50% | 35% | 35% | 35% | 35% | 35% | 35% | 50% | 50% | 50% | 50% | 50% | 50% | 15% | 15%
Mohammad Shadan | 69600 | Front End 1 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 20% | 20% | 10% | 10% | 25% | 25%
Mohammad Saif | 27000 | Front End 2 | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sunil Kumar | 73500 | Back End 1 | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 35% | 35% | 35% | 35% | 35% | 25% | 25%
- | 55200 | Gen Ai 1 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 25% | 15% | 15% | 15% | 25% | 25%
- | 21000 | Gen Ai 2 | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TBD (0.5) | 27000 | Data Engineer 2.2 | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
317700
OCE Team
Name | Cost | Skill | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Samarth | 33900 | Solution Owner | 50% | 50% | 50% | 50% | 35% | 35% | 35% | 35% | 35% | 35% | 50% | 25% | 25% | 25% | 15% | 15%
Sandeep Patil | 63000 | Front End 1 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 25% | 25%
Mohammad Saif | 27000 | Front End 2 | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
Pavan Padakki | 69000 | Back End 1 | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 25% | 25% | 25% | 25% | 25%
- | 54900 | Gen Ai 1 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 25% | 25% | 15% | 25% | 25%
- | 21000 | Gen Ai 2 | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
TBD (0.5) | 27000 | Data Engineer 2.2 | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
295800
All development ends on 22 May
Beta Luanch
National Luanch
Beta Luanch
National Luanch