## Sheet1
| Status | Remarks
Requirements Gathering & Finalization | Complete
MockUp | Complete
Data Assessment & Mapping | Complete
Infrastructure setup | Complete | Only Prod is Pending
DevOps Setup | Complete | Only Langfuse secrets mapping is Pending
Milestone Status
|  | Dev |  |  |  | QA | Beta Launch | Prod | National Launch | Remarks
|  | ETL (Dev) | BE (Dev) | FE (Dev) | GenAi (Dev)
Milestone 0 | Account Details , Smart Routing , Downloads , Query box , Related Questions, Citations | Complete | In progress (80%) | In progress (80%) | In progress (10%) |  | 2026-05-29 |  |  | i) All Features are complete, except Citations, which Genai/BE team is working on. Ii) GenAi Design and Development work started but slightly delayed, which team is working on to mitigate by adding one additional resource iii) Data Validation is in Progress
Milestone 1 | Top KPI , Action on KPI , Top Accounts, Account Search , Citations, follow up questions , Query Box, QnA (5 Questions) | Complete | In progress (80%) | In progress (80%) | In progress (10%) |  | 2026-05-29 |  |  | i) All Features are complete, except Citations, which Genai/BE team is working on. Ii) GenAi Design and Development work started but slightly delayed, which team is working on to mitigate by adding one additional resource iii) Data Validation is in Progress
Milestone 2 | Parent Acc Details , Opnal Readiness ,AccPerformance, QnA (2 Questions) | Complete | In progress (80%) | In progress (80%) | To be started |  | 2026-05-29 |  |  | i) GenAi development to be started ii) Data Validation is in Progress
Milestone 3 | Territory Insights : Filtering , Sorting , Download table, QnA (2 Questions) | In Progress (80%) | In progress (80%) | In progress (80%) | To be started |  | 2026-05-29 |  |  | i) GenAi development to be started ii) Data Validation is in Progress
Milestone 4 | Acct Heirarchy QnA (2 Questions) | Next Sprint | Next Sprint | Next Sprint | To be started |  | 2026-05-29

## Sheet2
Category | Milestone/Deliverable | Status |  |  |  | Comments/Updates
Development Pre-requisites | Requirements Gathering & Finalization | Complete |  |  |  | Awaiting Sign-Off
| MockUp | Complete |  |  |  | Awaiting Sign-Off
| Data Assessment & Mapping | Complete |  |  |  | Awaiting Sign-Off
| Infrastructure setup | Complete |  |  |  | Only Prod is Pending
| DevOps Setup | Complete |  |  |  | Only Langfuse secrets mapping is Pending
|  | Dev Status |  |  |  | Deployment ETA |  |  | Overall Status | Comments/Updates
|  | ETL | BE | FE | GenAI | Dev | QA | Prod
Development Milestone 0 | Account Details , Smart Routing , Downloads , Query box , Related Questions, Citations | Dev Complete (Validation in Progress) | In progress (90%) | In progress (80%) | NA | 2026-04-06 | 2026-05-15 | 2026-06-12 | At Risk | i) All Features are complete, except Citations and downloads, which Genai/BE team is working on
Development Milestone 1 | Top KPI , Action on KPI , Top Accounts, Account Search , Citations, Query Box, QnA (5 Questions) | Dev Complete (Validation in Progress) | In progress (70%) | In progress (80%) | In Progress (20%) | 2026-04-24 | 2026-05-15 | 2026-06-12 | At Risk | i) All Features are complete, except Citations, which Genai/BE team is working on. Ii) GenAi Design and Development work started but slightly delayed, which team is working on to mitigate in sprint 5 iii) Base Table Data Validation is in Progress iv) Semantic Layer development in progress v) Demo feedback to be implemented
Development Milestone 2 | Parent Acc Details, AccPerformance, Alerts Tracker QnA (2 Questions) | In progress (70%) | In progress (80%) | In progress (80%) | Next Sprint (Sprint 5) | 2026-05-08 | 2026-05-15 | 2026-06-12 | At Risk | i) GenAi development to be started ii) Alerts data ETL in progress
Development Milestone 3 | Territory Insights : Filtering , Sorting , Download table, QnA (2 Questions) | Dev Complete (Validation in Progress) | In progress (80%) | In progress (80%) | Next Sprint (Sprint 5) | 2026-05-08 | 2026-05-22 | 2026-06-12 | On Track | i) GenAi development to be completed ii) Data Validation is in Progress
Development Milestone 4 | Acct Hierarchy QnA (2 Questions) | Next Sprint (Sprint 5) | Next Sprint (Sprint 5) | Next Sprint (Sprint 5) | Sprint 6 | 2026-05-15 | 2026-05-22 | 2026-06-12 | On Track