## CallPlanner + RBD-DM Overview
Note: Phase 1 is required for initial deployment. Phase 2 for active development. Phase 3 for UAT / Production. No phase indicates we can reuse existing resource.
ID | Name | Resource | Description | Configuration | Environments (Note: UAT is a new environment) | Network Access Outbound (To) | Network Access Inbound (From) | Existing Infrastructure | Notes | Phase | Phase 1
1 | Postgres Database | AWS RDS | Postgres 16.3 | See Postgres Database (RDS) | Prod Dev |  | Resource #4 (API) Resource #20 (Chat API) | TRUE | Required changes in detail tab | - | EOW
2 | Kubernetes Cluster | AWS EKS Cluster | Kubernetes cluster to host applications | k8s v1.33 | Prod Dev UAT |  |  | TRUE | Some clusters are in the process of upgrading to v1.33 | -
2.1 | SCM Chat UI Repo | BitBucket | Source Code Management repo for CI/CD | TBD | - |  |  | FALSE | Per Jeremy we can work on the deployment repos after the basic builds are working | 2
2.2 | SCM Chat API Repo | BitBucket | Source Code Management repo for CI/CD | TBD | - |  |  | FALSE |  | 2
2.3 | Scaling platform monorepo | BitBucket | Source Code repo for application code | genai-platform | - |  |  | FALSE |  | 1
3 | Chat UI | AWS EKS/Chat UI | Artifact created from deployment | Instance t3a.medium (or equivalent) Replica: 2 100GB | Prod Dev UAT | Resource #4 (Rep API) Resource #20 (Chat API) | Browser (HTTPS) | FALSE | Included to highlight required networking configuration | 1
4 | Rep Agent API | AWS EKS/Rep Agent API | Docker Image |  | Prod Dev UAT | Resource #1 (DB) Resource #8 (Redshift) Resource #13 (S3) Resource #5 (Cube Dev) Resource #14 (OpenAI) | Browser (HTTPS) Resource #2 (Kubernetes cluster) Resource#20 (Chat API) | TRUE |  | -
5 | Semantic Cube Dev Server | AWS EC2 | Docker Image |  | Prod Dev |  | Resource #4 (Rep API) | TRUE |  | -
6 | Airflow ETL Server | AWS EC2 | Resource to execute ETL process |  | Prod Dev | Resource #1 (DB) Resource #19 (Airflow S3) Resource #18 (Elasticsearch server) Resource #100 (PSE Data Lake) |  | TRUE | Need to investigate if we need updates here, particularly around user management | -
7 | Sentry Server | EC2 | Docker Image | See Sentry | Prod Dev |  | Browser (HTTPS) Resource #20 (Chat API) | TRUE | Requires integration into Rep Agent API Requires prod resource | 2
8 | Langfuse Server | AWS EKS/Langfuse | Helm Chart | See Langfuse | Prod Dev |  | Resource #20 (Chat API) | TRUE | Requires configuring new applications in Langfuse | -
9 | Redshift Server | AWS Redhift Serverless | WorkGroup Version 1.0.80583 | See Redshift Serverless | Prod Dev |  | Resource #20 (Chat API) Resource #5 (Cube Dev) | TRUE |  | -
10 | Chat API DNS w/ HTTPS | Cloudflare + CNAME mapping | Cloudflare, Domain name for Chat API | api.genai-platform-<dev¦uat¦prod>.apps.jnj.com | Prod Dev UAT |  | for prod remove -prod (api.genai-platform.apps.jnj.com) | FALSE | We want to keep these distinct until we are fully ready to migrate the platform | 2
11 | Langfuse DNS w/ HTTPS | Domains/Langfuse | Cloudflare, Domain name for Langfuse UI/API |  | Prod Dev |  |  | TRUE |  | -
12 | Semantic Cube Dev DNS w/HTTPS | Domains/Cube Dev | Cloudflare, Domain name for Cube Dev UI/API |  | Prod Dev |  |  | TRUE |  | -
13 | Sentry DNS w/ HTTPS | Domains/Sentry | Cloudflare, Domain name for Sentry UI/API |  | Prod Dev |  |  | TRUE | Need to configure prod | 2
14 | CallPlanner S3 | S3 Bucket | S3 bucket for Callplanner resources | See S3 | Prod Dev |  |  | TRUE |  | -
15 | OpenAI Deployment | Azure OpenAI | Resource to create OpenAI endpoints in | See OpenAI | Prod Dev |  | Resource #20 (Chat API) | TRUE | Can reuse existing OpenAI deployments | -
16 | CDN S3 | S3 Bucket | S3 bucket for CDN resources | See S3 | Prod Dev UAT |  |  | TRUE |  | -
17 | Redis Server | AWS ElastiCache | Valkey v7.2 | See Redis Server (ElastiCache) | Prod Dev |  | Resource #20 (Chat API) | FALSE |  | 1
18 | OpenSearch Cluster | AWS OpenSearch | Elasticsearch 7.10 | See OpenSearch | Prod Dev |  | Resource #20 (Chat API) | FALSE | Currently we are leveraging the MSL resource, but a separate one is recommended | 1
19 | Airflow S3 | S3 Bucket | S3 Bucket for MWAA | See Airflow | Prod Dev |  | CICD Resource #6 (Airflow ETL) | TRUE |  | -
20 | Chat API | AWS EKS/Chat API | Artifact created from deployment | Instance: t3a.xlarge (or equivalent) Replica: 2 100GB | Prod Dev UAT | Resource #1 (DB) Resource #7/13 (Sentry/Sentry DNS) Resource #8/14 (Langfuse/Langfuse DNS) Resource #18 (Redis) Resource #19 (Elasticsearch) | Browser (HTTPS) Resource #6 (Airflow ETL) | FALSE | Included to highlight required networking configuration | 1
21 | Azure App Registration - Chat API Maps | Client registration to use maps services | Azure client app registration to use location services | See Location Services | Prod Dev |  |  | TRUE | Could reuse existing client configs | 2
22 | Azure App Registration - Chat API Voice | Client registration to use voice services | Azure client app registration to use voice services |  | Prod Dev |  |  | TRUE | Could reuse existing client configs | 2
23 | Azure App Registration - Chat UI / Chat API OAuth | Client registration to handle user OAuth | Azure client app registration for SSO / OAuth | JAN-APP-RBDDM-<DEV¦UAT¦PRD>-<ADMIN¦USER¦FIELD-USER> | Prod Dev UAT |  |  | FALSE | Each environment should have ADMIN, USER and FIELD-USER | 2
24 | Chat API DNS w/ HTTPS | Cloudflare + CNAME mapping | Domain name for internal network access | app.genai-platform-<dev¦uat¦prod>.apps.jnj.com | Prod Dev UAT |  | for prod remove -prod (app.genai-platform.apps.jnj.com) | FALSE | We want to keep these distinct until we are fully ready to migrate the platform | 2
25 | CICD | Jenkins |  |  | Prod Dev UAT |  |  | FALSE | We can probably reuse the existing Jenkings instance | 2
26 | Entra AD Groups | Entra AD | Access Directory resource group |  | Prod Dev UAT |  |  | FALSE |  | 2
API Gateway
Existing Infrastructure
100 | JnJ PSE Data Lake | RedShift Cluster |  |  | Prod Dev |  | Resource #6 (Airflow ETL) | TRUE
101 | Docker Repository | JFrog | Repository to publish Docker Images |  | Prod Dev UAT |  |  | TRUE

## Management App
ID | Name | Resource | Description | Configuration | Environments | Network Access Outbound (To) | Network Access Inbound (From) | Existing Infrastructure | Notes | Phase
1 | Platform Database | AWS RDS | Postgres 16.3 | See Postgres Database (RDS) | Prod UAT Dev |  | Resource #4 (API) | FALSE | Separate from scaling platform DB | 1
2 | Kubernetes Cluster | AWS EKS Cluster | k8s v1.33 | Add Configuration Details | Prod UAT Dev |  |  | FALSE | Optional: can keep management app and other apps in the same cluster | 1
| SCM Chat UI Repo | [6 empty] | FALSE | Per Jeremy we can work on the deployment repos after the basic builds are working | 2
| SCM Chat API Repo | [6 empty] | FALSE |  | 2
3 | Management UI | AWS EKS/Chat UI | Docker Image |  | Prod UAT Dev | Resource #21 (Management API) | Browser (HTTPS) | FALSE | Included to highlight required networking configuration | 1
4 | Management API | AWS EKS/Chat API | Docker Image |  | Prod UAT Dev | Resource #1 (DB) Resource #7/13 (Sentry/Sentry DNS) Resource #18 (Redis) | Browser (HTTPS) | FALSE | Included to highlight required networking configuration | 1
5 | Secrets Manager | AWS Secret Manager |  |  | Prod UAT Dev |  |  | FALSE |  | 1
6 | IAM Roles | AWS IAM roles for secrets manager |  |  | Prod UAT Dev |  |  | FALSE |  | 1
7 | Redis Server | AWS ElastiCache | Valkey v7.2 | See Redis Server (ElastiCache) | Prod UAT Dev |  | Resource #4 (API) | FALSE | Can reuse if sharing cluster | -
8 | Management API DNS w/ HTTPS | Domains/Chat API | Domain name for Chat API | app.genai-admin-<dev¦uat¦prod>.apps.jnj.com | Prod UAT Dev |  |  | FALSE |  | 2
9 | Management UI DNS w/ HTTPS | Domains/Chat API | Domain name for Chat API | api.genai-admin-<dev¦uat¦prod>.apps.jnj.com | Prod UAT Dev |  |  | FALSE |  | 2
10 | Entra AD Group | Entra | Access Directory resource group |  | Prod UAT Dev |  |  | FALSE |  | 2
11 | Azure App Registration - Management UI / API OAuth | Client registration to handle user OAuth | Azure client app registration for SSO / OAuth | JAN-APP-MGMT-<DEV¦UAT¦PRD>-ADMIN | Prod UAT Dev |  |  | FALSE |  | 2
12 | Sentry
13 | API Gateway
Existing Infrastructure
100 | Docker Repository | JFrog | Repository to publish Docker Images
101 | CICD | Jenkins + Jfrog
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required config? Deploy to same kube cluster?
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: other IAM roles?

## Postgres Database (RDS)
Note: required changes include new schemas and capacity.
Name | Value | Section | Note | Existing Infrastructure
Engine | PostgreSQL | Engine options |  | TRUE
Engine Version | Postgres 16.4 or equivalent | Engine options |  | TRUE
Multi-AZ | 1 | Availability and durability | Multi-AZ only needed for production (2) | TRUE
DB cluster identifier | genai-platform-[prod¦uat¦dev] | Settings |  | TRUE
Master username | master | Settings |  | TRUE
Credential management | AWS Secrets Manager* | Credential Settings | Whatever is easiest to integrate with k8s secrets | TRUE
DB Instance class | Standard classes - db.t4g.medium | Instance configuration | db.m7g.large or db.m7g.xlarge may be needed depending on data ETL | TRUE
Storage type | GP3 | Storage |  | TRUE
Allocated Storage | 100 | Storage | 400GB for prod | FALSE
Provisioned IOPS | 3000 | Storage | 12000 for prod | TRUE
Storage througput | 125 | Storage | 500 for prod | TRUE
FALSE
FALSE
Group Name | genai-platform-[prod]-pg16 | Create Parameter Group |  | TRUE
Group Description | genai-platform-[prod]-pg16 | Create Parameter Group |  | TRUE
Engine Type | PostgreSQL | Create Parameter Group |  | TRUE
Parameter group family | postgres16 | Create Parameter Group |  | TRUE
Enable auto minor version upgrade | No |  |  | FALSE
FALSE
shared_preload_libraries | pg_stat_statements,pg_tle,auto_explain,pg_cron,pglogical | Parameter |  | TRUE
FALSE
FALSE
FALSE
DATABASES | Notes |  |  | FALSE
callplanner | Primary database for platform |  | Currently scoped to env (e.g. callplanner_). We can make this consistent across environments but in the meantime need to create a new DB that can be deleted later | FALSE
langfuse | Used for langfuse, can create separate user/pass for langfuse to use |  |  | FALSE
callplanner_<env¦prod> |  |  |  | TRUE
FALSE
SCHEMA NAMES |  |  |  | FALSE
public |  |  |  | FALSE
auth |  |  |  | FALSE
brandinsights |  |  |  | FALSE
jnj |  |  |  | FALSE
ref |  |  |  | FALSE
workspace |  |  |  | FALSE
callplanner |  |  |  | TRUE
genai |  |  |  | FALSE
FALSE
EXTENSIONS |  |  |  | FALSE
pg_trgm |  |  |  | FALSE
uuid-ossp |  |  |  | FALSE
pgcrypto |  |  |  | FALSE
pgvevctor |  |  |  | FALSE
plpgsql |  |  |  | TRUE

## Airflow
Name | Value | Section
Name | genai-platform-[prod¦dev]-mwaa | Details
Dags Folder |  | DAG Code in S3
Requirements file | requirements.txt | DAG Code in S3
Class | mw1.medium | Environment Class
Minimum Worker Count | 2 | Environment Class
Maximum Worker Count | 10 | Environment Class
Scheduler Count | 2 | Environment Class
Minimum Webserver Count | 2 | Environment Class
Maximum Webserver Count | 2 | Environment Class
Airflow task Logs | Enabled | Monitoring
Airflow web server logs | Enabled | Monitoring
Airflow scheduler logs | Enabled | Monitoring
Airflow worker logs | Enabled | Monitoring
Airflow DAG processing logs | Enabled | Monitoring
Airflow task log level | INFO | Monitoring
Airflow web server log level | INFO | Monitoring
Airflow scheduler log level | INFO | Monitoring
Airflow worker log level | INFO | Monitoring
Airflow DAG processing log level | INFO | Monitoring
core.dags_are_paused_at_creation | False | Airflow Configuration Options
core.test_connection | True | Airflow Configuration Options
secrets.backend | airflow.providers.amazon.aws.secrets.secrets_manager.SecretsManagerBackend | Airflow Configuration Options
secrets.backend_kwargs | {connections_prefix=airflow/connections, variables_prefix=airflow/variables} | Airflow Configuration Options
Secrets (In Secrets Manager)
airflow/connections/msl_db | postgresql://postgres:[PASSWORD]@[HOST]:5432/postgres
airflow/connections/es_conn | elasticsearch://[USER]:[PASSWORD]@[HOST]:[PORT]/https

## OpenAI
OpenAI App
Setting | Value
Name | openai-genai-platform-[prod¦dev]
Location | East US
Deployments
Name | gpt-4o-mini
Model | gpt-4o-mini
Model Version | 2024-07-18
Capacity | 100k TPM

## Sentry
NOTE
Jeremy recently set this up for Rep and the process may differ.
DOCUMENTATION
https://develop.sentry.dev/self-hosted/
SENTRY GITHUB
https://github.com/getsentry/self-hosted/releases/tag/24.11.2
Requires valid SSL certificate, nginx reverse proxy or have AWS ELB
User Authentication can be configured with SAML SSO or User/Pass
EC2 Specs
Instance Name | genai-platform-[prod¦dev]
Instance Type | t3a.xlarge
Storage | 300GB EBS
AMI | Linux, Latest Debian/Ubuntu
UPDATE LIMITS
echo "
* soft nofile 131072
* hard nofile 131072
* soft nproc 8192
* hard nproc 8192
root soft nofile 131072
root hard nofile 131072
root soft nproc 8192
root hard nproc 8192" ¦ sudo tee /etc/security/limits.d/nofile.conf
echo "vm.max_map_count=524288" ¦ sudo tee -a /etc/sysctl.conf
echo "fs.file-max=131072" ¦ sudo tee -a /etc/sysctl.conf
sudo sysctl -p
INSTALLATION
VERSION="24.11.2"
git clone https://github.com/getsentry/self-hosted.git
cd self-hosted
git checkout ${VERSION}
sudo ./install.sh --skip-user-creation
sentry/config.yml
system.url-prefix: "https://sentry.domain.com"
sentry/sentry.conf.py
CSRF_TRUSTED_ORIGINS = ["https://sentry.domain.com", "http://127.0.0.1:9000"]
SECURE_PROXY_SSL_HEADER = ('HTTP_X_FORWARDED_PROTO', 'https')
USE_X_FORWARDED_HOST = True
SESSION_COOKIE_SECURE = True
CSRF_COOKIE_SECURE = True
SOCIAL_AUTH_REDIRECT_IS_HTTPS = True

## Redis Server (ElastiCache)
ElastiCache Valkey
Name | Value | Section | Note
Deployment option | Design your own cache | Configuration
Creation method | Cluster cache | Configuration
Cluster mode | Disabled | Cluster Info
Cluster name | msl-copilot-[production¦sandbox] | Cluster Info
Location | AWS Cloud | Location
Multi-AZ | Enabled | Location | Multi-AZ not needed for sandbox
Engine Version | 7.2 | Cluster settings
Node type | cache.t4g.medium | Cluster settings
Number of replicas | 2 | Cluster settings
Access control | AUTH default user access | Security
AUTH token | - | Security | Generate randomly

## S3
Name | Description | Notes | Configuration
com.jnj.genai-platform.[prod¦dev¦uat].cdn | CDN Bucket
com.jnj.genai-platform.[prod¦dev¦uat].airflow | Airflow Bucket | No public access
CORS policy | Configuration to allow applications HTTPS access |  | Access to Chat UI and API, Management UI and API across each environment

## Langfuse
Documentation
https://langfuse.com/self-hosting/kubernetes-helm
Sizing
t3a.medium equivalent
Environment Variables
PORT | 3005
AUTH_AZURE_AD_CLIENT_ID
AUTH_AZURE_AD_CLIENT_SECRET
AUTH_AZURE_AD_TENANT_ID
DATABASE_URL | postgres://[USER]:[PASSWORD]@[HOST]:5432/langfuse
NEXTAUTH_URL |  | DNS the site will run on
NEXTAUTH_SECRET |  | Generate randomly - openssl rand -base64 32
SALT |  | Generate randomly - openssl rand -hex 32
ENCRYPTION_KEY |  | Generate randomly - openssl rand -hex 32
AUTH_DISABLE_USERNAME_PASSWORD | true
AUTH_DISABLE_SIGNUP | false
Note: Azure app is used for authentication. Can re-use the same one being used for the copilot. Access to projects/data needs to be provisioned in langfuse iteself.

## OpenSearch cluster
OpenSearch
Name | Value | Section | Note
Domain name | genai-platform-[dev¦uat¦prod] | Name
Domain creation method | Standard create | Domain creation method
Templates | Dev/test | Templates
Demployment option | Domain without standby | Deployment options
AZ | 1 | Deployment options | 2 for prod
OpenSearch version | 3.2 | Engine options
Instance Family | General purpose | Number of data nodes
Instance type | m7g.large.search
Data nodes | 1
Storage | EBS - GP3
Storage size per node | 250GB
Total throughput per node | 250MiB/s
Network | VPC Access | Network
IP address type | IPv4 only | Network
Enable fine-grained access control | Yes | Fine-grained access control | Create master user
Master username | genai-copilot | Fine-grained access control
Master password | [GENERATE] | Fine-grained access control
Confirm master password | [GENERATE] | Fine-grained access control
Domain access policy | Only use fine-grained access control | Access Policy

## Redshift Serverless
Redshift Serverless
Name | Value | Section | Note
Cluster Name | genai-platform-[prod] | Cluster Info
Cluster Mode | serverless | Cluster Info
WorkGroup Name | genai-platform-[prod]-wg | Workgroup Info
WorkGroup Version | 1.0.80583 | Configuration
Base Capacity | 128 RPUs | Configuration
WorkGroup Patch Version | Patch 186 | Configuration

## Location Services
Azure Maps Account
Name | msl-copilot-[prod¦dev]-maps-resource
Resource | ?? Might need to create one
Subscription | ?? Might need to create one
Identity | msl-copilot-[prod¦dev]-maps-identity
Note: can reuse existing configs as well
Azure Managed Identity
Name | genai-platform-[prod¦dev]-maps-identity
Azure Role Assignments
Role | Azure Maps Search and Render Data Reader
Resource | enai-platform-[prod¦dev]-maps-resource
Resource Type | Azure Maps Account
Assigned To | genai-platform-[prod¦dev]-maps-identity
* Use existing App registration
App Registration | GenAI Platform - PROD
** Add the App Registration as an owner of the Azure Maps Account in the Microsoft Graph. **
Need the following details after creation:
Maps Account name
Maps Account Subscription ID
Maps Account Subscript Key
App Registration Client ID
App Registration Client Secret
Principal ID for the Identity created
Tenant ID where the resources are hosted
Resource Group name where the resources are hosted