## Sheet1
S. NO | Iteam | Access Level | Environment | Status | Comments
1
2
3

## Sheet2
FRM Scaling Platform Migration
Name | Status | Dev | QA | Prod
Infrastructure provisioning |  | 8th May | 8th May
Technology Fitment and alignment of FRM app into Scaling platform |  | 12th May
Redesign within Scaling to accommodate FRM functionality. |  | 15th May
Landing Page (Dev) |  | 15th May
Withme CRM setup |  | 20th May
Account Insights (search + deep dive) |  | 22nd May
Subitems
QA testing for Account Insights |  |  | 27th May
Territory and DEP Insights |  | 3rd June
QA testing for Territory and DEP Insights |  |  | 9th June
Policy Search |  | 12th June
QA testing for Policy Search |  |  | 17th June
Load testing |  |  | 19th June
FRM UAT |  |  | 25th June
Prod Deployment - Productionization of the FRM app into the Scaling Platform |  |  |  | 8th July
Smoke Testing with one FRM in prod |  |  |  | 10th July
⭐ FRM User Directed to Scaling Platform PROD |  |  |  | 14th July
Smart routing enablement |  |  |  | 16th July