## High Level Plan_Updated_1Dec (hidden)
|  | Tasks / Week Ending (WE) | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30
Initiation, Planning & Kick Off | bar: 2025-10-24
SP Code Base Migration (Trinity to JnJ) | bar: 2025-10-24
Rep Co-Pilot Code Base (Hardened) Migration (Trinity to JnJ) | bar: 2025-10-24
Infrastructure Requirement Finalization, Provisioning & Setup | bar: 2025-10-31 to 2025-11-14
Bit Bucket Repo and CI CD Approach Finalization | bar: 2025-10-31 to 2025-11-07
CI CD Pipeline Development - Scaling, Repco | bar: 2025-11-07 to 2025-11-14
Scaling Application Deployment in Dev | bar: 2025-11-14 to 2025-12-05
RepCo Application Deployment in Dev | bar: 2025-11-14 to 2025-12-05
MSL - Lung (Configuration) | bar: 2025-12-05
Repco - Lung (Configuration) | bar: 2025-12-05
QA Movement & Validation (Scaling) | bar: 2025-12-12
QA Movement & Validation (Repco) | bar: 2025-12-12
Hardening (Internalization) - Repco JPH (existing) - Validation | bar: 2025-12-05 to 2025-12-19
Hardening (Internalization) - MSL | bar: 2025-12-05 to 2025-12-19
|  | Testing & UAT Sign Off | 2025-12-26: Yearly Shut down
Pre-CutOver
Cut Over (Repco , MSL)
Rep Co-Pilot Phase in/Phase out in Prod (Decomissioning) - TBD
Team | Resources
Infra | Abhyuday, Khaja, Vasu Team,
Prod Team | Muthu, Vasu Team
Testing Team
Notes:
SP - Scaling platform
We are here.
Completed - Code Base Migration, Bitbucket Repo & & CI CD Approach Finalization .
In Progress -Infrastructure additional requirements, URLs are being provisioned along with Pipeline work
We are here.
We are here.
Completed - Code Base Migration, Bitbucket Repo & & CI CD Approach Finalization .
In Progress -Infrastructure additional requirements, URLs are being provisioned along with Pipeline work
Delay of a week, hence pushed the date to 5th Dec
Added new line items for MSL and Repco - Lung
We are here.
This MSL and Repco Lung configurations is dependent on Scaling App Readiness in Dev

## High Level Plan (hidden)
|  |  | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11
Initiation, Planning & Kick Off | bar: 2025-10-12
SP Code Base Migration (Trinity to JnJ) | bar: 2025-10-12
Rep Co-Pilot Code Base (Hardened) Migration (Trinity to JnJ) | bar: 2025-10-19
Infrastructure Requirement Finalization, Provisioning & Setup | bar: 2025-10-19 to 2025-10-26
CI CD Approach Finalization and Establishment | bar: 2025-10-19 to 2025-11-02
Scaling Application Deployment | bar: 2025-10-26 to 2025-11-02
RepCo Application Deployment | bar: 2025-11-09 to 2025-11-16
QA Movement & Validation | bar: 2025-11-16 to 2025-11-23
Hardening (Internalization) - MSL, Repco JPH, | bar: 2025-11-16 to 2025-11-30
Testing & UAT Sign Off | bar: 2025-11-16 to 2025-12-07
Pre-CutOver
Cut Over
Parallel Run
Rep Co-Pilot Phase in/Phase out in Prod (Decomissioning) | bar: 2026-01-11
Team | Resources
Infra | Abhyuday, Khaja, Vasu Team,
Prod Team | Muthu, Vasu Team
Testing Team
Notes:
SP - Scaling platform

## High Level Plan_Updated_24Dec
| Tasks / Week Ending (WE) | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10
| Initiation, Planning & Kick Off | 2025-12-26: YEARLY SHOTDOWN
Hardening | SP Code Base Migration (Trinity to JnJ) | bar: 2025-10-24
Hardening | Rep Co-Pilot Code Base (Hardened) Migration (Trinity to JnJ) | bar: 2025-10-24
Hardening | Infrastructure Requirement Finalization, Provisioning & Setup | bar: 2025-10-31 to 2025-11-14
Hardening | Bit Bucket Repo and CI CD Approach Finalization | bar: 2025-10-31 to 2025-11-07
Hardening | CI CD Pipeline Development - Scaling, Repco | bar: 2025-11-07 to 2025-11-14
Hardening | Scaling Application Deployment in Dev | bar: 2025-11-14 to 2025-12-05
Hardening | Scaling -QA Movement & Validation | bar: 2025-12-05 to 2025-12-19
RBD/DM | RBD DM Application Deployment in Dev (Tremfya GI) | bar: 2025-11-14 to 2025-12-05
RBD/DM | RBD DM-QA Movement & Validation (Tremfya GI) | bar: 2025-12-05 to 2025-12-19
RBD/DM | RBD DM-Beta Launch (Tremfya GI) | bar: 2025-12-12 to 2025-12-19; 2026-01-02
RBD/DM | RBD DM Prod Launch (Tremfya GI) | bar: 2026-01-09 to 2026-01-30
RBD/DM | RBD DM National Launch (Tremfya GI) | bar: 2026-01-30
RBD/DM | RBD DM Beta Launch (Lung) | bar: 2026-01-30 to 2026-02-06
RBD/DM | RBD DM Prod Launch (Lung) | bar: 2026-02-13
RBD/DM | RBD DM National Launch (Lung) | bar: 2026-02-20
RBD/DM | RBD DM Beta Launch (Caplyta & GU) | bar: 2026-01-30 to 2026-02-06
RBD/DM | RBD DM Prod Launch (Caplyta & GU) | bar: 2026-02-13
RBD/DM | RBD DM National Launch (Caplyta & GU) | bar: 2026-02-20
FRM | FRM National Launch (Erleada)
FRM | FRM Hardening /Porting | bar: 2026-02-20 to 2026-03-06
FRM | FRM Regression Testing | bar: 2026-03-13
FRM | FRM Prod Deploy | bar: 2026-03-13 to 2026-03-20
FRM | FRM Old App Sunset | bar: 2026-03-27
Repco | RepCo Erleada Application Deployment in Dev | bar: 2025-11-14 to 2025-12-05
Repco | Repco Erleada QA Movement & Validation | bar: 2025-12-05 to 2025-12-19
Repco | Repco - Lung (Configuration) | bar: 2025-12-12 to 2025-12-19; 2026-01-02
Repco | Repco - GU (Configuration) | bar: 2025-12-12 to 2025-12-19; 2026-01-02 to 2026-01-16
Repco | Repco - H&N (Configuration) | bar: 2025-12-12 to 2025-12-19; 2026-01-02 to 2026-01-23
Repco | Repco -Regression testing (If JPH is being decommissioned, no testing needed) | bar: 2025-12-19; 2026-01-02
Repco | Repco -Performance testing for all Brands | bar: 2026-01-02 to 2026-01-09
Repco | Repco - Productionization | bar: 2026-01-16 to 2026-01-23
Repco | Repco - Prod Launch | bar: 2026-01-16
Repco | Repco - Sunset of Repco Old | bar: 2026-02-13 to 2026-02-20
MSL | MSL - Lung (Configuration) in Dev | bar: 2025-12-12 to 2025-12-19; 2026-01-02
MSL | MSL - GU (Configuration) in Dev | bar: 2026-01-02 to 2026-01-16
MSL | MSL - HN (Configuration) in Dev | bar: 2026-01-09 to 2026-01-23
MSL | MSL - Hardening (Internalization) - MSL | bar: 2026-01-02 to 2026-01-23
MSL | MSL - Porting of all Brands including Lung, Derm, Mood into New MSL | bar: 2026-01-30
MSL | MSL -Regression testing for all Brands | bar: 2026-02-06 to 2026-02-13
MSL | MSL -Performance testing for all Brands | bar: 2026-02-06 to 2026-02-13
MSL | MSL - Productionization | bar: 2026-02-13 to 2026-02-20
MSL | MSL - Prod Launch | bar: 2026-02-13 to 2026-02-20
MSL | MSL - Sunset of MSL Old | bar: 2026-02-20 to 2026-03-06
Currently not in scope for Hardening (will be part of enhancement / maintenance work)
Software Upgrade | Scaling - Software Upgrade of the CoPilot Version - GPT 4 to GPT 5 | bar: 2026-01-30
Software Upgrade | Repco - Software Upgrade of the CoPilot Version - GPT 4 to GPT 5 | bar: 2026-01-30; 2026-04-03
Software Upgrade | MSL - Software Upgrade of the CoPilot Version - GPT 4 to GPT 5 | bar: 2026-01-30
Software Upgrade | Regression testing after Software Upgrade | bar: 2026-01-30
I - Connect | Scaling - I connect
I - Connect | Repco I Connect
I - Connect | MSL - I Connect
Documentation | bar: 2026-02-06
Sign-Off and Transition to Maintenance | bar: 2026-02-06 to 2026-02-13
Rep Co-Pilot Phase in/Phase out in Prod (Decomissioning) - TBD
MSL Lung Beta Launch - 9th Jan
MSL H&N Beta Launch - TBD
MSL GU Beta Launch - TBD
MSL Hardening Completeion - 3rd/4th Week Jan
MSL Porting All brands - 3rd/4th Week Jan
MSL Regression Testing - 1st/2nd Week Feb
MSL Performance Testing- 1st/2nd Week Feb
Rep Erleada Prod Deploy
Sunset of Old MSL Application - 1st/2nd Week March
CI CD Development Completion
Infrastructure Completion
Code Base MIgration Completion
Scaling App Deployment - Dev
Scaling App Deployment - QA
Repco Erleada App Deployment - Dev
Repco App Deployment - QA 12/24
Repco GU Beta Launch - TBD
Repco H&N Beta Launch - TBD
MSL Productionization & Prod Launch
Software Upgrade of GPT 4 to 5 and Regression Testing
I Connect Configuration and Enablement for All Co-Pilot Applications
Maintenance Phase
Documentation and KT and Handover to Maintence Phase
We are Here
RBD DM App Deployment - Dev (Tremfy
RBD DM App Deployment - QA (Tremfya)
RBD DM Beta Launch (Tremfya)
RBD DM Prod Launch (Tremfya)
RBD DM National Launch -(Tremfya)
RBD DM Prod Launch - Captyla & GU
RBD DM National Launch - Captyla & GU
RBD DM Beta Launch - Captyla & GU
RBD DM Prod Launch - Lung
RBD DM National Launch- Lung
RBD DM Beta Launch - Lung
FRM Hardeining
FRM Regression
FRM National Launch (Erleada)
Rep Erleada Config Compete
Rep Erleada National Sales Meeting (1/12)
Completed
Completed
Completed
Completed
Completed
Completed
Completed
Rep Erleada Beta Launch (1/12)
Completed
Completed
In progress
Rep Erleada National Launch - 1/26

## Sheet2
|  | Non -Scaling |  |  |  |  | Scaling
|  | In Dev | In QA | Prod | Status | In Dev | In QA | Prod | Status
Tasks / Week Ending (WE)
Initiation, Planning & Kick Off
Hardening | SP Code Base Migration (Trinity to JnJ)
Hardening | Rep Co-Pilot Code Base (Hardened) Migration (Trinity to JnJ)
Hardening | Infrastructure Requirement Finalization, Provisioning & Setup
Hardening | Bit Bucket Repo and CI CD Approach Finalization
Hardening | CI CD Pipeline Development - Scaling, Repco
Hardening | Scaling Application Deployment in Dev |  |  |  |  | 2026-12-12 |  |  | Completed
Hardening | Scaling -QA Movement & Validation | [5 empty] | 2026-12-19 |  | Completed
RBD/DM | RBD DM Application Deployment in Dev (Tremfya GI) |  |  |  |  | 2026-12-12 |  |  | Completed
RBD/DM | RBD DM-QA Movement & Validation (Tremfya GI) | [5 empty] | 2026-12-19 |  | Completed
RBD/DM | RBD DM-Beta Launch (Tremfya GI) | [5 empty] | 2026-01-22 |  | In progress
RBD/DM | RBD DM Prod Launch(Tremfya GI) | [6 empty] | 2026-02-16
RBD/DM | RBD DM National Launch (Tremfya GI) | [6 empty] | 2026-02-26
RBD/DM | RBD DM Application Deployment in Dev (Lung)
RBD/DM | RBD DM Beta Launch (Lung)
RBD/DM | RBD DM Prod Launch (Lung)
RBD/DM | RBD DM National Launch (Lung)
RBD/DM | RBD DM Beta Launch (Caplyta & GU)
RBD/DM | RBD DM Prod Launch (Caplyta & GU)
RBD/DM | RBD DM National Launch (Caplyta & GU)
FRM | FRM Application Deployment in Dev (Tremfya GI)
FRM | FRM-QA Movement & Validation (Tremfya GI)
FRM | FRM-Beta Launch (Tremfya GI)
FRM | FRM Prod Launch (Tremfya GI) |  | 2026-02-13 |  |  |  | 2026-03-13
FRM | FRM National Launch (Erleada) |  | 2026-02-13 |  |  |  | 2026-03-13
FRM | FRM Old App Sunset
Repco | RepCo Erleada Application Deployment in Dev | [5 empty] | 2026-12-12
Repco | Repco Erleada QA Movement & Validation | [5 empty] | 2026-12-24
| Repco Erleada QA Beta Launch | [5 empty] | 2026-01-12
| Repco Erleada QA National Launch | [5 empty] | 2026-12-26
Repco | Repco - Lung (Configuration)
Repco | Repco - GU (Configuration)
Repco | Repco - H&N (Configuration)
Repco | Repco -Regression testing (If JPH is being decommissioned, no testing needed)
Repco | Repco -Performance testing for all Brands
Repco | Repco - Productionization
Repco | Repco - Prod Launch
Repco | Repco - Sunset of Repco Old
MSL | MSL - Lung (Configuration) in Beta Launch | 2026-01-15
| MSL - Lung (Configuration) in National Launch |  | 2026-01-26
MSL | MSL - H&N (Configuration) in Beta Launch | 2026-01-19
MSL | MSL - H&N (Configuration) in National Launch |  | 2026-02-09
MSL | MSL - GU (Configuration) in Beta Launch | 2026-01-21
MSL | MSL - GU (Configuration) in National Launch |  | 2026-02-05
MSL | MSL - Porting of all Brands including Lung, Derm, Mood into New MSL | [5 empty] | 2026-03-30
MSL | MSL -Regression testing for all Brands | [5 empty] | 2026-03-30
MSL | MSL -Performance testing for all Brands | [5 empty] | 2026-03-30
MSL | MSL - Productionization
MSL | MSL - Prod Launch
MSL | MSL - Sunset of MSL Old

## Updated_Timelines
|  | Remarks | Non -Scaling | [5 empty] | Scaling
|  |  | In Dev | Dev Status | In QA | QA Status | Prod | Prod Status | In Dev | Dev Status | In QA | QA Status | Prod | Prod Status
Scaling | Infrastructure Requirement Finalization, Provisioning & Setup (Dev & QA) | [7 empty] | 2026-11-15 | Completed | 2026-11-21 | Completed | 2026-11-21 | Completed
Scaling | Bit Bucket Repo and CI CD Approach Finalization | [7 empty] | 2026-11-21 | Completed | 2026-11-21 | Completed | 2026-11-21 | Completed
Scaling | CI CD Pipeline Development - Scaling, Repco | [7 empty] | 2026-11-21 | Completed | 2026-11-21
Scaling | Scaling Application Deployment in Dev | [7 empty] | 2026-12-12 | Completed
Scaling | Scaling -QA Movement & Validation | [9 empty] | 2026-12-19 | Completed
Scaling | Infrastructure Requirement Finalization, Provisioning & Setup (Prod)
Scaling | Scaling -Prod Movement & Validation | [11 empty] | 2026-01-21
RBD/DM | RBD DM Application Deployment in Dev (Tremfya GI) | Currently Built on Scaling Platform | [6 empty] | 2026-12-12 | Completed
RBD/DM | RBD DM-QA Movement & Validation (Tremfya GI) | Currently Built on Scaling Platform | [8 empty] | 2026-12-19 | Completed
RBD/DM | RBD DM-Beta Launch (Tremfya GI) | Currently Built on Scaling Platform | [8 empty] | 2026-01-22 | In progress
RBD/DM | RBD DM Prod Launch(Tremfya GI) | Currently Built on Scaling Platform | [10 empty] | 2026-02-16
RBD/DM | RBD DM National Launch (Tremfya GI) Prod | Currently Built on Scaling Platform | [10 empty] | 2026-02-26
FRM | FRM Application Deployment in Dev (Erleada) | Currently Not built on Scaling Platform | 2026-01-06 | Completed
FRM | FRM-QA Movement & Validation (Erleada) | Currently Not built on Scaling Platform |  |  | 2026-01-08 | In progress
FRM | FRM-Beta Launch (Erleada) | Currently Not built on Scaling Platform |  |  | 2026-01-08 | In progress
FRM | FRM Prod /National Launch (Erleada) | Currently Not built on Scaling Platform |  |  |  |  | 2026-01-26
FRM | FRM Application Deployment in Dev (Tremfya GI) | Currently Not built on Scaling Platform | 2026-01-12 | In progress
FRM | FRM-QA Movement & Validation (Tremfya GI) | Currently Not built on Scaling Platform |  |  | 2026-01-15
FRM | FRM-Beta Launch (Tremfya GI) | Currently Not built on Scaling Platform |  |  | 2026-01-15
FRM | FRM Prod/National Launch (Tremfya GI) | Currently Not built on Scaling Platform |  |  |  |  | 2026-01-26
FRM - Scaling | Spinning up of New FRM Copilot Chat- API (into the Scaling Platform) | Currently Not built on Scaling Platform | [10 empty] | 2026-02-10
FRM - Scaling | Pointing the New FRM API to the existing DB | Currently Not built on Scaling Platform | [10 empty] | 2026-02-17
FRM - Scaling | Configuration of Prisma Client/Connection | Currently Not built on Scaling Platform | [10 empty] | 2026-02-24
FRM - Scaling | Configuration of New FRM Copilot chat API to work with its Own DB | Currently Not built on Scaling Platform | [10 empty] | 2026-03-03
FRM - Scaling | Porting changes from and all the Brands to Existing FRM Copilot to the New FRM Copilot Chat API | Currently Not built on Scaling Platform | [10 empty] | 2026-03-17
FRM- Scaling | Prod Deploment - Productionization of the FRM app into the Scaling Platform | Currently Not built on Scaling Platform | [10 empty] | 2026-03-25
Repco | RepCo Erleada Application Deployment in Dev | Currently Built on Scaling Platform | [6 empty] | 2026-12-12 | Completed
Repco | Repco Erleada QA Movement & Validation | Currently Built on Scaling Platform | [8 empty] | 2026-12-24 | Completed
Repco | Repco Erleada Beta Launch | Currently Built on Scaling Platform | [8 empty] | 2026-01-12
Repco | Repco Erleada National Launch (Prod) | Currently Built on Scaling Platform | [10 empty] | 2026-01-26
MSL | MSL - Lung (Configuration) in Dev | Currently Not built on Scaling Platform | 2026-12-24 | Completed
MSL | MSL - Lung (Configuration) in Beta Launch | Currently Not built on Scaling Platform |  |  | 2026-01-15 | In Progress
MSL | MSL - Lung (Configuration) in Prod/National Launch | Currently Not built on Scaling Platform |  |  |  |  | 2026-01-26
MSL | MSL - H&N (Configuration) in Dev | Currently Not built on Scaling Platform
MSL | MSL - H&N (Configuration) in Beta Launch | Currently Not built on Scaling Platform |  |  | 2026-01-19
MSL | MSL - H&N (Configuration) in Prod/National Launch | Currently Not built on Scaling Platform |  |  |  |  | 2026-02-09
MSL | MSL - GU (Configuration) in Dev | Currently Not built on Scaling Platform
MSL | MSL - GU (Configuration) in Beta Launch | Currently Not built on Scaling Platform |  |  | 2026-01-21
MSL | MSL - GU (Configuration) in Prod/National Launch | Currently Not built on Scaling Platform |  |  |  |  | 2026-02-05
MSL | MSL - Caplyta (Configuration) in Dev | Currently Not built on Scaling Platform
MSL | MSL - Caplyta Beta Launch (QA) | Currently Not built on Scaling Platform |  |  | 2026-01-21
MSL | MSL - Caplyta Prod/National Launch (Prod) | Currently Not built on Scaling Platform |  |  |  |  | 2026-02-05
MSL- Scaling | Spinning up of New MSL Copilot Chat- API (into the Scaling Platform) | Currently Not built on Scaling Platform | [10 empty] | 2026-02-10
MSL- Scaling | Pointing the New MSL API to the existing DB | Currently Not built on Scaling Platform | [10 empty] | 2026-02-17
MSL- Scaling | Configuration of Prisma Client/Connection | Currently Not built on Scaling Platform | [10 empty] | 2026-02-24
MSL- Scaling | Configuration of New MSL Copilot chat API to work with its Own DB and further configuration MSL Copliot Chat API as an Agent | Currently Not built on Scaling Platform | [10 empty] | 2026-03-03
MSL- Scaling | Porting changes from and all the Brands to Existing MSL Copilot to the New MSL Copilot Chat API | Currently Not built on Scaling Platform | [10 empty] | 2026-03-17
MSL- Scaling | Prod Deployment -Productionization of the MSL app into the Scaling | Currently Not built on Scaling Platform | [10 empty] | 2026-03-25

## Abhyuday remarks (hidden)
Folder structure - whatever done so far, correct Dockerfile contents - needs to be updated, according to the changes discussed tonight's group call. Dockerfile has been removed from inside field_insights_ai_v2 folder, it should be retained there. In the repo root a copy needs to be prepared with updates. scm_config -> folder name expected _scm_config scm_helm -> folder name expected _scm_helm scm_jenkins -> folder name expected _scm_jenkins All internal files under the _scm* folders need to be written - take up as your immediate next task.
Dockerfile - 2 Dockerfile instances created, one in repo root (as per yesterday's discussion) and one more in _scm_container/RBD-DM-management-ui/. The 2nd one looks more logical, we can discard the one not required after validation. _scm_config -> values - for common-values: ports opened at 3000 (as per the original repcopilot configuration) for dev.values, qa.values and prod.values: URL needs to be updated as per the new URL for RBD/DM (as of now pointing towards Repcopilot) Everywhere currently project code is used as JICE, it can be updated once new code is received (discussion already on going) automation-pipeline.yaml - teamKey needs to be updated once new project code is received
All configurations under _scm_helm YAML files are connected to FRM copilot instead of Repco - this was discussed and aligned. We shall let it be FRM for now to ensure it does not fight with the existing repco. _scm_helm > values.yaml --------- container port is set to 8000, but container port as per Container.yaml is 3000 Why this difference? _scm_helm > templates files will make sense once we have the path details from dev team. we can change the FRM references as well as updated the paths that time together.
App ID - get a clarity on this and update Your configuration files refer to predev.values.yaml - this one does not exist. Do we need this? then we need to create. If not, then we need to remove the reference. dev.values.yaml, qa.values.yaml, prod.values.yaml - all these are referring to old repcopilt repository, need to be updated to current repo, i.e. copilot-management-ui deploy_qa.groovy and deploy_prod.groovy - remote url is set to 'https://sourcecode.jnj.com/scm/asx-jice/rep-copilot-ui.git', needs to be updated deploy_qa.goovvy, deploy_prod.goovvy => spelling is wrong, remove extra 'v'

## Sheet1 (hidden)
 | time axis 2025-10-12 to 2026-01-09
Stream | App/Platform |  | Activities | time axis 2025-10-12 to 2026-01-09
| General |  | Intiation, High Level Planning | bar: 2025-10-12 to 2025-10-15
| General |  | Kick Off | bar: 2025-10-15
DevOps & JnJ Infra | General | Code Base Migration | BitBucket Creation in JJ & SetUp | bar: 2025-10-14 to 2025-10-15
DevOps & JnJ Infra | Scaling | Code Base Migration | Obtaining Access Request for Trinity Github & JJ Bitbucket | bar: 2025-10-14 to 2025-10-15
DevOps & JnJ Infra | Scaling | Code Base Migration | Migrating the Scaling Platform Code Base from Trinity Github to JJ Bitbucket | bar: 2025-10-15 to 2025-10-16
DevOps & JnJ Infra | Scaling | Code Base Migration | Repco - Obtaining and Migrating the Repco Code Base from Trinity Github to JJ Bitbucket | bar: 2025-10-17
DevOps & JnJ Infra | General | Infra Provisioning | Collecting and Finalizing the Infra Requirements | bar: 2025-10-14 to 2025-10-27
DevOps & JnJ Infra | General | Infra Provisioning | Requesting InfraStructure & SetUp | bar: 2025-10-17 to 2025-10-27
DevOps & JnJ Infra | Scaling | CI CD Approach Finalization | Repo strcuture and deployment finalization | bar: 2025-10-23 to 2025-10-29
DevOps & JnJ Infra | General | CI CD Pipeline Development | CI CD for the Scaling Platform | bar: 2025-10-23 to 2025-11-06
Scaling | Scaling | Scaling App Deployment | Scaling Application Code - Script Compilation, Execution, Deployment in JnJ Dev | bar: 2025-11-04 to 2025-11-07
Scaling | Scaling | Scaling App Deployment | Scaling Application Code - Regression Testing in JnJ Dev | bar: 2025-11-05 to 2025-11-11
DevOps & JnJ Infra | Repco | CI CD Pipeline Development | CI CD for the Repco Platform | bar: 2025-10-30 to 2025-11-10
RepCo | RepCo | Repco App Deployment | Repco Application Code - Script Compilation, Execution, Deployment in JnJ Dev | bar: 2025-11-07 to 2025-11-13
RepCo | RepCo | Repco App Deployment | Repco Application Code - Regression Testing in JnJ Dev | bar: 2025-11-11 to 2025-11-14
MSL | MSL | MSL App Deployment | MSL Application Code - Script Compilation, Execution, Deployment in JnJ Dev | bar: 2025-11-14 to 2025-11-19
MSL | MSL | MSL App Deployment | MSL Application Code - Regression Testing in JnJ Dev | bar: 2025-11-17 to 2025-11-20
RepCo | RepCo | Repco - Existing App Code Sync Up | Repco Application Code Sync Up with Existing Version in JnJ - Code Merge in JnJ Dev | bar: 2025-11-21 to 2025-11-26
RepCo | RepCo | Repco - Existing App Code Sync Up | Repco Application Code Sync Up with Existing Version in JnJ - Regression Testing in JnJ Dev | bar: 2025-11-26 to 2025-12-01
MSL | MSL | MSL - Existing App Code Sync Up | MSL Application Code Sync Up with Existing Version in JnJ - Code Merge in JnJ Dev | bar: 2025-12-02 to 2025-12-05
MSL | MSL | MSL - Existing App Code Sync Up | MSL Application Code Sync Up with Existing Version in JnJ - Regression Testing in JnJ Dev | bar: 2025-12-08 to 2025-12-11
|  | Pre Cut Over | Parallel Run and Data Validation Wherever possible | bar: 2025-12-12 to 2025-12-24
|  | Cut Over | Code Freeze for all the Apps | bar: 2025-12-22 to 2025-12-25
|  | Cut Over | Productizing the Code | bar: 2025-12-24 to 2025-12-25
Scaling | Scaling | Cut Over | Scaling - Prod Deployment & Validation | bar: 2025-12-25 to 2026-01-01
RepCo | RepCo | Cut Over | Repco - Prod Deployment & Validation | bar: 2025-12-25 to 2026-01-01
MSL | MSL | Cut Over | MSL - Prod Deployment & Validation | bar: 2025-12-25 to 2026-01-01
|  | Cut Over | Sign Off for Deployment & Decommisioning | bar: 2026-01-02 to 2026-01-05
Decommisioning | bar: 2026-01-06 to 2026-01-09
Code Migration Completeion - Completed on time
Infra Provisioning Completion - Delay of 2 Days as on 21st Oct
DevOps CI CD Completion - Scaling
Scaling App Deployment Completion
Repco App Deployment Completion
MSl App Deployment Completion
Repco App Deployment Completion
MSL App Deployment Completion
Code Freeze for all Apps
Prod Deployment Completeion for All Apps
Decommissioning Completeion for All Apps
CI CD Deployment approach finalization- Delay of 2 Days as on 27thOct
DevOps CI CD Completion - Repco

## Challenges (hidden)
S. No | Item | Description | resolution steps | Days | status | Solution | Next Step
1 | Infrastructure Requirements Finalization | It took more time in finalizing the Infra requirements
2 | Deployment Approach | Deployment Approach due to Mono Repo Approach |  |  |  |  | Access for Xena, waiting for approval to understand the Jnj approach
3 | Bitbucket restriction | .env files are being used in this repository of Scaling platform. But .env files in bitbucket is restricted |  |  |  | Hence, either the frontend code will need some changes to remove the .env dependency, or we’ll need formal approval to continue using them.
4 | ARG Command Usage | Docker File |  |  |  | Dedicated having a call with Jonathan, Jeremy to be consulted on regular basis
challanges bringing up locally
| env | figuring out the correct env for all the apps | 1. figuring out actual env required for JNJ env and we have created few env by ourself 2. initial request for all infra requested but few infra was missed/left over because assuming it is not required. | 3-4 days | Done
| infra | after figuring the env we came to know additional infra | 1. requested additnal infra
| pnpm install | Dev team was unable to install due to npm registry issue | 1.few commands are given by JJIT to resolve this issue and it got resolved | 2 dyas | Done
| connectivity issue | Redis is througing the ssl issue on local | connectivity issue resolevd but still issue is coming now |  | Done
| Database prisma migration | team faced a migration issue while installing locally | 1.when we are trying to run the application we faced this schema errors. those schemas we cannot create it by ourself so we rasied a request with JJIT to create it. 2. in the mean time we tried using local postgres DB by using docker image and tried but still we faced migration issues. 3.team tried chnages the schemas one by one | 3 days | Done
| prisma scehema and extensions | Team came to know the prisma and extension in DB after running the application | we rasie extensions of DB with JJIT because it was throuing extension issue like pgtrgm . | 2 days | Done
Deployment challanegs
| folder structure for monorepo and deployment related scripts | root repo re arrangement based on JNJ standards and pushing all images to JJFT jfrog | 1.created all deployement related scripots as per the mono repo standard of JNJ. and worked on building the images with initial code which is transferred to JNJ and images were created | 2days | Done
| Jfrog repo chnage | keeping all the in JJFT Jfrog | 1. initialy it was aligned to keep all the docker images in JJFT jfrog repo so modified the scripts in same format but later they said to keep scaling related in scaling jforg repo and management in management repo so modified based on that but later during the access for cross repo it is said that to keep all images at jjft(mgmt jfrgo repo) and created jjft pull secrtes in scaling cluster | 3-4 days | Done
| new code migration after the chnages | code is modified in trinity and pushed to jnj. | 1. here it is getting issue with build the docker image due to packages
| IAM polices | To define policy aliagning with JNJ complience | created the Iam policy and gave it them but JJIT team said to give the exact requirememt of application so team conneted and disscussed and gave the requirement | 3 days
| JPM role access for cross deployment | as it needs to be deployed in two different cluster JPM role (jenkins) need to have access to respective cluster and Jfrog | connected with JJIT team and clarified on it | 1 day | Done
| Rearrangement of dockerfile | as we brought the src from apps folder to root repo Dockerfile and refernces should be changed as per that process | we have re arranged the dockerfile and tried building it. it was build with Initial code base but facing build failures due to new migrated code base | 2 days | inprogress
| aws secrets |  | once we are able to run locally we can goahead with same ENV's to get added as secrets | 1 day | pending

## Challenges_Updatd (hidden)
S. No | Item | Description | Resolution steps | No Of Days Consumed | Status | Impact
1 | env files | Figuring out the correct env for all the apps | 1. figuring out actual env required for JNJ env and we have created few env by ourself 2. initial request for all infra requested but few infra was missed/left over because assuming it is not required. | 8 days | Done | Planned for 1 day, but consumed 7 days more.
2 | infra | After figuring the env we came to know additional infra | 1. requested additnal infra
3 | pnpm install | Dev team was unable to install due to npm registry issue | 1.few commands are given by JJIT to resolve this issue and it got resolved | 2 dyas | Done | Unexpected Task
4 | connectivity issue | Redis is througing the ssl issue on local | connectivity issue resolevd but still issue is coming now |  | Done | Unexpected Task
5 | Database prisma migration | Team faced a migration issue while installing locally | 1.when we are trying to run the application we faced this schema errors. those schemas we cannot create it by ourself so we rasied a request with JJIT to create it. 2. in the mean time we tried using local postgres DB by using docker image and tried but still we faced migration issues. 3.team tried chnages the schemas one by one | 3 days | Done | Unexpected Task
6 | prisma scehema and extensions | Team came to know the prisma and extension in DB after running the application | we rasie extensions of DB with JJIT because it was throuing extension issue like pgtrgm . | 2 days | Done | Unexpected Task
7 | folder structure for monorepo and deployment related scripts | root repo re arrangement based on JNJ standards and pushing all images to JJFT jfrog | 1.created all deployement related scripots as per the mono repo standard of JNJ. and worked on building the images with initial code which is transferred to JNJ and images were created | 2days | Done | Planned for 1 day, but consumed 1 day more.
8 | Jfrog repo chnage | keeping all the in JJFT Jfrog | 1. initially it was aligned to keep all the docker images in JJFT jfrog repo so modified the scripts in same format but later they said to keep scaling related in scaling jforg repo and management in management repo so modified based on that but later during the access for cross repo it is said that to keep all images at jjft(mgmt jfrgo repo) and created jjft pull secrtes in scaling cluster | 3-4 days | Done | Unexpected Task
9 | new code migration after the changes | code is modified in trinity and pushed to jnj. | 1. here it is getting issue with build the docker image due to packages |  |  | Unexpected Task
10 | IAM polices | To define policy aliagning with JNJ complience | created the Iam policy and gave it them but JJIT team said to give the exact requirememt of application so team conneted and disscussed and gave the requirement | 3 days |  | Unexpected Task
11 | JPM role access for cross deployment | as it needs to be deployed in two different cluster JPM role (jenkins) need to have access to respective cluster and Jfrog | Connected with JJIT team and clarified on it | 1 day | Done | Unexpected Task
12 | Rearrangement of dockerfile | as we brought the src from apps folder to root repo Dockerfile and refernces should be changed as per that process | we have re arranged the dockerfile and tried building it. it was build with Initial code base but facing build failures due to new migrated code base | 2 days | inprogress | Unexpected Task
13 | AWS secrets |  | Once we are able to run locally we can goahead with same ENV's to get added as secrets | 1 day | pending
14 | ENV for APP's | Application is having the build time env not the run time | After the deployment Application is not able to use run time var's from pod.chalenge we are facing now is when we are passing the env through place holder to management-app it is working but trinity values are harded in src code it seems. so it will break for Iconnect. chat-ui it is looking for hard code config file during the build time. if we go with place holder Zod validation should be removed but if we do so it will not work for iconnect. | 3 daya | in progress | Unexpected Task
15 | Nginx | there was a file ningx.conf in config which is define to do reverse proxy but here in jnj we use ingress | there was nginx conf by which it is doing the reverse proxy so commented the reverse proxy to use ingress | 1 day | done | Unexpected Task
16 | SRc changes to work locally | Src code is chnaged by dev team to make it work locally | to connect to aws secrets just to work locally team has requested for aws keys and made a modification in src code to work locally | 2 days | done | Unexpected Task
17 | ingress issue | Admission controllers are not rendereing the svc | ingress admission controllers was not rendering the ingress svc. | 1 day | done | Unexpected Task
18 | CORS issue | cors issue for the aplication | cors issue -we have deployed the app with internal and external ingress but as suggested by JJIT we have kept only external ingress later found out internal url is not working because of external ingress so we have again depoyed internal and external ingress for chat-api | 3 days | done | Unexpected Task
19 | CONTENT SECRURITY POLICY | CSP policy is not working | we have commented out the code for csp. we have taken it as backlog item |  | pending
20

## Actions (hidden)
S. No | Task | Date | Attendees
1 | Kick Off | 16th Oct | JP, Vasu & Team, Abyuday, Khaja, Jonathan, Subidya, Kishore
2
1. Bitbucket Repository Setup
We need to request the creation of five repositories under a single Bitbucket project named scaling-platform. The proposed repository names are:
scaling-platform-chat-ui
scaling-platform-chat-api
scaling-platform-management-app
scaling-platform-management-api
scaling-platform-veeva-zip (for Veeva integration)
Once the naming convention is cofirmed with Jonathan, will reach out to Subidya for the Repo creation process
2. Code Migration
Once the repositories are created, developers will begin migrating the respective code from the existing copilot-management-api repository into the newly created ones.
3. EKS Environment Access & Deployment URLs
As per Sekar’s latest email, the Dev EKS environment has been set up. Raised the access request and once granted, we’ll be able to inspect the actual infrastructure endpoints.
Sekar has also provisioned an NGINX Load Balancer. We still need to finalize deployment URLs:
For management-app and management-api, we require a host URL.
For chat-ui and chat-api, the Scaling Platform team will decide on appropriate URLs.
4. Jenkins Setup & Access
Jenkins setup is in progress. Once ready, we’ll need to raise an AD Group access request for Jenkins.
5. JFrog Repository Request
There is currently no JFrog repository for the Scaling Platform. We need to raise a request for a separate JFrog repo. Once created, the team will share the AD Group ID, and we’ll proceed to raise an access request.
6. Deployment Preparation
Deployment script preparation